## Changing main table
No. | Problem | Akshay's comment | Proposed solution
Action 1 | Selects load circle, with MainTable 1 and saves
Action 2 | Configures at least one step in any one circle (from Consolidation to Publish)
Action 3 | Unselects the circle and saves the job
Action 4 | Changes main table to MainTable2 and saves the job
Action 5 | Again selects Consolidation.
Result | Then user will see previously configured steps stored against MainTable1 | Because we don't delete steps when user selects and save. We won't be changing that in this story.
Conflicting scenarios
1 | So if we don't delete then when I am checking in the backend whether there is at least one step configured anywhere between Consolidation to Publish, then even though these circles, user won't be able to change main table. | Risk is less but user has to delete those steps wherever they are present, before changing main table. | 1) We don't make any new change apart from what is mentioned in the story i.e. changing main table depends on Load Data selected but also on any step configured between Consolidation to Publish OR 2) We could prevent changing main table irrespective of which circle is saved.
2 | If we allow user to change just because circle is unselected (even though at least one configuration exists in the backend) then that configuration will become invalid and will result into error on ADB. | Risk is high with job failing on ADB.

## estimation
Story Id | Title | Assignee | Started date | Estimate (days) | Approx deadline | Testing buffer | Actual deadline
SSDL-10685 | Basic Detail changes | Akshay | 2022-02-21 | 2 | 2022-02-22 | 4 | 2022-02-28
SSDL-10917 | .NET maintenance changes | Akshay/Vishal S | 2022-02-21 | 2 | 2022-02-22
SSDL-10701 | Project Setup part 1 | Gopinadh | 2022-02-18 | 13 | 2022-03-08 | 3 | 2022-03-10
SSDL-10913 | Custom column UI + API changes | Vishal S | 2022-02-24 | 7 | 2022-03-04
SSDL-10690 | Load data changes | Akshay |  | 1
SSDL-10694 | Consolidation changes | Akshay | 2022-03-01 | 7 | 2022-03-09
SSDL-10697 | Profile changes | Vishal S | 2022-03-07 | 5 | 2022-03-11
SSDL-10700 | VNE changes | Vishal S | 2022-03-14 | 5 | 2022-03-18
SSDL-10699 | Classify changes | Vishal S/Gopi | 2022-03-11 | 6 | 2022-03-18
SSDL-10698 | Publish changes | Vishal S | 2022-03-21 | 4 | 2022-03-24
SSDL-10696 | Import Utility changes | Akshay | 2022-03-10 | 1 | 2022-03-10
SSDL-10695 | Export Utility changes | Akshay | 2022-03-11 | 1 | 2022-03-11
SSDL-10759 | RWB changes | Vishal K |  | 3
SSDL-10606 | ADB & .NET Integration | Gopi/Vishal S/Akshay | 2022-03-10 | 8 | 2022-03-21
SSDL-10907 | Message processing for schema change part 1 | Pratik |  | 13
SSDL-10921 | API automation with postman | ? |  | ?
|  |  |  | QC deadline (max) | 2022-03-24
|  |  |  | UAT | 2022-04-08
|  |  |  | Prod | 2022-04-15
Formulas:
Approx deadline = WORKDAY([Started date], [Estimate (days)] - 1)
Actual deadline = WORKDAY([Approx deadline], [Testing buffer])
Actual deadline = WORKDAY([Approx deadline], [Testing buffer]) -1